## Technical Debt
Tab | Item | Category | Status | Owner | Notes
Auth & RBAC | Implement Google Auth with invitational RBAC | Integration | Archived | Dhruman | Scope: Google OAuth + invite-only signup. Deliverable: role assignment at invite acceptance and enforcement in UI/API.
Auth & RBAC | Ensure H has full admin/owner access | Feature | Complete | Dhruman | Scope: Owner role permissions. Deliverable: full access across all modules and settings.
Auth & RBAC | Add user hierarchy support | Feature | Complete | Dhruman | Scope: parent/child role hierarchy. Deliverable: cascading visibility and approvals by hierarchy.
Billing | Add payment and enable paid features | Integration | Not started | Dhruman | Scope: billing integration and feature gating. Deliverable: payment flow and subscription-based access control.
Deployment | Publish/update site after receiving invite | Integration | Complete | Dhruman | Scope: production deployment. Deliverable: latest build published and invite flow verified.
Units | Import CSV to create units | Integration | Complete | Dhruman | Scope: CSV import for units. Deliverable: validation, mapping, and bulk creation workflow.
Assets | Add assets by asset type | Feature | Complete | Dhruman | Scope: asset catalog + types. Deliverable: backend tables and UI to create assets by type.
Assets | Fix location description retype behavior | Feature | Complete | Dhruman | Scope: input UX bug. Deliverable: stable editing without resets or data loss.
Assets | Restrict asset creation to admin for now | Feature | Complete | Dhruman | Scope: permissions. Deliverable: admin-only create/edit on assets.
Assets | Seed 5 catch basins for Eros to inspect | Integration | Complete | Dhruman | Scope: demo data. Deliverable: 5 catch basin assets with notes for inspection.
Issues | Fix Issue tab unresponsive behavior | Tech Debt | Complete | Dhruman | Scope: UI responsiveness. Deliverable: issue tab actions/inputs responsive and stable.
Permits | Connect permits data source | Integration | Not started | Dhruman | Scope: permits integration. Deliverable: data fetch + display from permits system.
Permits | Fix typing issue in permits | Tech Debt | Complete | Dhruman | Scope: form input bug. Deliverable: typing/editing works without lag or loss.
Permits | Coordinate with Eros to fetch all permits (email) | Integration | Not Started | Dhruman | Scope: external dependency. Deliverable: complete permits dataset received from Eros.
Chat | Improve chat UI | Feature | Complete | Dhruman | Scope: layout, readability, and usability. Deliverable: cleaner chat UI with consistent spacing and affordances.
Voice Agents | Add 2nd voice agent tool integration | Integration | Not started | Dhruman | Scope: voice agent provider integration. Deliverable: ElevenLabs configured and available in app.
Voice Agents | Store API keys and permissions (Vapi or Retool) | Integration | Not started | Dhruman | Scope: secure key storage + permissioning. Deliverable: admin-managed API keys and access controls.
Voice Agents | Create issue workflow from customer call to work order | Feature | Complete | Dhruman | Scope: workflow automation. Deliverable: call -> issue -> supervisor -> inspector -> work order pipeline.
Organization | Decide placement of Organization tab (settings) | Feature | Complete | Dhruman | Scope: navigation IA. Deliverable: final placement and routing for Organization in settings.
Contacts | Add CRM contacts management | Feature | Complete | Dhruman | Scope: CRM contacts CRUD. Deliverable: manage team and stakeholder contacts.
Contacts | Add per-user CRM data sharing opt-in/out | Feature | Archived | Dhruman | Scope: privacy controls. Deliverable: per-user sharing preference enforced.
Contacts | Define property manager role behaviors | Feature | Complete | Dhruman | Scope: role policy. Deliverable: permissions and responsibilities documented and enforced.
Contacts | Model roles: resident, property manager team, R4 | Feature | Complete | Dhruman | Scope: role taxonomy. Deliverable: roles created and mapped to permissions.
Contacts | Connect portal users to CRM; remove GoHighLevel | Integration | Complete | Dhruman | Scope: CRM integration. Deliverable: portal users synced to CRM; GoHighLevel retired.
Doc Center | Implement doc center with locked docs (no CRUD) | Feature | Complete | Dhruman | Scope: read-only doc center. Deliverable: locked documents with access control.
Doc Center | Dump all docs to GDrive; use as system of record | Integration | Complete | Dhruman | Scope: storage migration. Deliverable: all docs centralized in Google Drive.
Doc Center | Extract all project attachments and dump to GDrive | Integration | Not started | Dhruman | Scope: attachment extraction. Deliverable: all attachments archived in Drive.
Doc Center | Generate unified document list | Feature | Not started | Dhruman | Scope: indexing. Deliverable: consolidated doc inventory listing.
Doc Center | Admin-only: pull necessary docs from GDrive to app | Feature | Not started | Dhruman | Scope: admin curation. Deliverable: selective sync from Drive into app.
Daily Inspections | Connect assets to daily inspections (grid view) | Feature | Complete | Dhruman | Scope: inspection UI + asset linkage. Deliverable: grid view with asset selection.
Daily Inspections | Store inspection history | Feature | Complete | Dhruman | Scope: data persistence. Deliverable: historical inspection records stored and searchable.
Daily Inspections | Link inspections to issues and supervisor review | Feature | Complete | Dhruman | Scope: workflow. Deliverable: inspections create issues and route to supervisor.
Projects | Implement Procorlite lifecycle feature (mock project) | Feature | Not started | Dhruman | Scope: lifecycle module. Deliverable: mock project with lifecycle states and transitions.
Roles | Set Dhruman as Super Admin | Feature | Complete | Dhruman | Scope: role assignment. Deliverable: super admin permissions applied to Dhruman.
Roles | Set H as Owner | Feature | Complete | Dhruman | Scope: role assignment. Deliverable: owner permissions applied to H.
Roles | Set Simi as property manager/admin with suspend/assign | Feature | Complete | Dhruman | Scope: role assignment. Deliverable: admin permissions with suspend/assign capabilities.
Roles | Set Eros as Inspector / Superintendent Admin Clerk | Feature | Complete | Dhruman | Scope: role assignment. Deliverable: inspector and admin clerk permissions set.
Roles | Add contractor outside contract role (later) | Feature | Complete | Dhruman | Scope: future role. Deliverable: contractor role defined for later rollout.
Knowledge | Get and read Nspire book; apply to dev | Integration | Archived | Dhruman | Scope: knowledge alignment. Deliverable: guidance extracted and applied to product decisions.
General | Reset index.html as per PM APAS | Feature | Completed | Dhruman | Scope: branding polish. Deliverable: app title set to PM APAS.